## Risk assesment
Risk ID (number) | Type of Risk | Description of Hazard | Description of Consequence or Effect | Pre- mitigation |  |  | Mitigations
|  |  |  | Frequeny | Consequence | Risk number
1 | Techincal | Battery overheat or fire | Could damage other electrical components | 1 | 5 | 5 | Current sensor
2 | Techincal | Electrical short circuits | Electrical components damaged - need to be reordered | 2 | 3 | 6 | Read documnetations for correct connections
3 | Techincal | Telemetry bugs and issues | May send incorrect commands to control unit | 3 | 2 | 6 | Efficient and collaborative coding
4 | Techincal | Noise affecting radio link | No or oncorrect commands sent to control unit | 2 | 4 | 8 | Antennas to be exposed from RC car
5 | Techincal | Thermal expansion | Aerodynamic shell or other componenet may be damaged | 1 | 5 | 5 | Use materials with low expanding coefficient
6 | Techincal | Overheating electrical components | Electrical components damaged - need to be reordered | 2 | 3 | 6 | Use of heat sink or other suitbible heat dissapation methods
7 | Scheduling | Parts order delay | Time pressure for assembly and test | 2 | 2 | 1 | Order early
8 | Scheduling | Design and integration | Compexity of fitting all components into RC car | 3 | 1 | 3 | Planning and coordination with other teams
9 | Scheduling | Software development | May take longer than expected | 3 | 1 | 3 | Efficient and collaborative coding
10 | Scheduling | Sensor calibration | Sensors may be unreliable - multiple types may need to be tested | 3 | 2 | 6 | Review technical documents to find sensor with best specifications
11 | Scheduling | Testing delays | Time pressure for record attempt | 3 | 2 | 6 | Planning and scheduling
12 | Financial | Component costs | Over budget | 3 | 2 | 6 | Sponsorships
13 | Financial | Shipping costs | Over budget | 3 | 1 | 3 | NA
14 | Financial | Software costs | Over budget | 3 | 2 | 6 | NA
15 | Financial | Workshop costs | Over budget | 3 | 2 | 6 | NA